## deploy_plan
Month | Release | QA | UAT | PROD | Change ID
202103 | SAM 2.86 | 03/03 CHN Time | 03/10 CHN Time | 03/17 CHN Time | CHG0060045 - SAM China Release 2.86-UAT
CHG0060046 - SAM China Release 2.86-CN PROD
202103 | SAM 2.86.5 | 03/18 CHN Time | 03/19 CHN Time | 03/31 CHN Time | CHG0060047 - SAM China Month-End Release 2.86.5-UAT
CHG0060048 - SAM China Month-End Release 2.86.5-PROD
202103 | FO Local Release 2.86 | 03/03 CHN Time | 03/10 CHN Time | 03/17 CHN Time | CHG0060049 - FO China Local Release 2.86-UAT
CHG0060050 - FO China Local Release 2.86-PROD
202103 | FO Local Release 2.86.5 | 03/18 CHN Time | 03/19 CHN Time | 03/31 CHN Time | CHG0060051 - FO China Local Release 2.86.5-UAT
CHG0060052 - FO China Local Release 2.86.5-PROD
202104 | SAM 2.87 | 04/06 CHN Time | 04/13CHN Time | 04/20 DAL Time | CHG0060573-SAM China Release 2.87-UAT
CHG0060572-SAM China Release 2.87-CN PROD
202104 | SAM 2.87.5 | 04/21 CHN Time | 04/22 CHN Time | 04/30 DAL Time | CHG0060575-SAM China Month-End Release 2.87.5-UAT
CHG0060576-SAM China Month-End Release 2.87.5-PROD
202104 | FO Local Release 2.87 | 04/06 CHN Time | 04/13CHN Time | 04/20 DAL Time | CHG0060577-FO China Local Release 2.87-UAT
CHG0060579-FO China Local Release 2.87-PROD
202104 | FO Local Release 2.87.5 | 04/21 CHN Time | 04/22 CHN Time | 04/30 DAL Time | CHG0060581-FO China Local Release 2.87.5-UAT
CHG0060582-FO China Local Release 2.87.5-PROD
202105 | SAM 2.88 | 05/06 CHN Time | 05/12 CHN Time | 05/19 CHN Time | CHG0060813 - SAM China Release 2.88-UAT
CHG0060814 - SAM China Release 2.88-CN PROD
202105 | SAM 2.88.5 | 05/20 CHN Time | 05/21 CHN Time | 05/31 CHN Time | CHG0061535- SAM China Month-End Release 2.88.5-UAT
CHG0061536- SAM China Month-End Release 2.88.5-PROD
202105 | FO Local Release 2.88 | 05/06 CHN Time | 05/12 CHN Time | 05/19 CHN Time | CHG0061533-FO China Local Release 2.88-UAT
CHG0061534- FO China Local Release 2.88-PROD
202105 | FO Local Release 2.88.5 | 05/20 CHN Time | 05/21 CHN Time | 05/31 CHN Time | CHG0061531-FO China Local Release 2.88.5-UAT
CHG0061532-FO China Local Release 2.88.5-PROD
202106 | SAM 2.89 | 06/04 CHN Time | 06/10 CHN Time | 06/17 DAL Time | CHG0061609 - SAM China Release 2.89-UAT
CHG0061610 - SAM China Release 2.89-CN PROD
202106 | SAM 2.89.5 | 06/18 CHN Time | 06/21 CHN Time | 06/30 DAL Time | CHG0061611 - SAM China Month-End Release 2.89.5-UAT
CHG0061612 - SAM China Month-End Release 2.89.5-PROD
202106 | FO Local Release 2.89 | 06/04 CHN Time | 06/10 CHN Time | 06/17 DAL Time | CHG0061613 - FO China Local Release 2.89-UAT
CHG0061614 - FO China Local Release 2.89-PROD
202106 | FO Local Release 2.89.5 | 06/18 CHN Time | 06/21 CHN Time | 06/30 DAL Time | CHG0061615 - FO China Local Release 2.89.5-UAT
CHG0061616 - FO China Local Release 2.89.5-PROD

## links
发布相关
Octopus | https://deploy/app#/Spaces-1/
Jenkins | http://10.216.212.98/job/FO/job/SAM/job/release/
Service Now | https://marykay.service-now.com/nav_to.do
Create Branch | http://ads.mkcorp.com/DefaultCollection/FrontOffice/_versionControl?path=%24%2FFrontOffice%2FRELEASE
Create Package | http://ads.mkcorp.com/DefaultCollection/FrontOffice/_build
中国日历 | https://mkcorp.sharepoint.com/sites/mkc_IT/sam/frontoffice/default.aspx
美国日历 | https://mkcorp.sharepoint.com/sites/co-usa-ist-dbssamfo/Lists/Calendar/Release.aspx
测试Links
玫琳凯之窗-PROD | https://www.marykayintouch.com.cn/login/login.aspx
玫琳凯之窗-QA | https://qa-site.marykayintouch.com.cn/login/login
玫琳凯之窗-UAT | https://uat-site.marykayintouch.com.cn/login/login
国家企业信用信息公示系统 | http://www.gsxt.gov.cn/index.html
Citrix网页版 | https://citrix.mkcorp.com.cn/vpn/index.html
Splunk系统 | http://mksplunk.chn.mkcorp.com/zh-CN/account/login
工作Link
MK工时系统 | https://marykay.tenrox.net/TEnterprise/index.asp
博彦工时系统 | https://e-cology.beyondsoft.com/login/Login.jsp
新MK文件系统 | https://wiki.chn.mkcorp.com/pages/viewpage.action?pageId=61579549
旧MK文件系统 | https://marykay.atlassian.net/wiki/spaces/FCQKB/overview
MQ_DEV | http://fo-rmq.ebz-chn-dev.mkaws.com:15672
MQ_QA | http://fo-rmq.ebz-chn-qa.mkaws.com:15672
MQ_UAT | http://fo-rmq.ebz-chn-uat.mkaws.com:15672

## SQL
查询DIQ | select top 10 cp.ConsultantNumber,cp.ContactID,cp.SubsidiaryID from ConsultantProfile cp (nolock) inner join ConsultantCareerLevel ccl (nolock) on cp.ContactID = ccl.ConsultantID inner join (select DIQID,du.BeginDate from DIQUnits du (nolock) where du.Status = 1 -- Active group by du.DIQID,du.BeginDate) diqUnits on cp.ContactID = diqUnits.DIQID where ccl.LevelID = 300 and ccl.Date = '2016-10-01' and diqUnits.BeginDate < '2016-10-01'
查询DIR | SELECT top 10 cp.ConsultantNumber,cp.ContactID,ccl.LevelID,dtsd.SeniorDirectorID FROM ConsultantCareerLevel ccl (nolock) inner join ConsultantProfile cp (nolock) on ccl.ConsultantID = cp.ContactID inner join DirectorUnits du WITH (NOLOCK) on ccl.ConsultantID = du.DirectorID inner join DirectorToSeniorDirector dtsd (nolock) on du.DirectorID = dtsd.DirectorID and dtsd.Date = ccl.Date WHERE ccl.Date = '2016-10-01' AND ccl.LevelID between 400 and 499 AND du.DebutDate < '2016-10-01' AND (du.TerminationDate >= '2016-10-01' OR du.TerminationDate IS NULL)