## home
Home
CAM

## Release_Plan
Month | Release | QA | UAT | PROD | Change ID
202103 | SAM 2.86 | 03/03 CHN Time | 03/10 CHN Time | 03/17 CHN Time | CHG0060045 - SAM China Release 2.86-UAT
CHG0060046 - SAM China Release 2.86-CN PROD
202103 | SAM 2.86.5 | 03/18 CHN Time | 03/19 CHN Time | 03/31 CHN Time | CHG0060047 - SAM China Month-End Release 2.86.5-UAT
CHG0060048 - SAM China Month-End Release 2.86.5-PROD
202103 | FO Local Release 2.86 | 03/03 CHN Time | 03/10 CHN Time | 03/17 CHN Time | CHG0060049 - FO China Local Release 2.86-UAT
CHG0060050 - FO China Local Release 2.86-PROD
202103 | FO Local Release 2.86.5 | 03/18 CHN Time | 03/19 CHN Time | 03/31 CHN Time | CHG0060051 - FO China Local Release 2.86.5-UAT
CHG0060052 - FO China Local Release 2.86.5-PROD
202104 | SAM 2.87 | 04/06 CHN Time | 04/13CHN Time | 04/20 DAL Time | CHG0060573-SAM China Release 2.87-UAT
CHG0060572-SAM China Release 2.87-CN PROD
202104 | SAM 2.87.5 | 04/21 CHN Time | 04/22 CHN Time | 04/30 DAL Time | CHG0060575-SAM China Month-End Release 2.87.5-UAT
CHG0060576-SAM China Month-End Release 2.87.5-PROD
202104 | FO Local Release 2.87 | 04/06 CHN Time | 04/13CHN Time | 04/20 DAL Time | CHG0060577-FO China Local Release 2.87-UAT
CHG0060579-FO China Local Release 2.87-PROD
202104 | FO Local Release 2.87.5 | 04/21 CHN Time | 04/22 CHN Time | 04/30 DAL Time | CHG0060581-FO China Local Release 2.87.5-UAT
CHG0060582-FO China Local Release 2.87.5-PROD
202105 | SAM 2.88 | 05/06 CHN Time | 05/12 CHN Time | 05/19 CHN Time | CHG0060813 - SAM China Release 2.88-UAT
CHG0060814 - SAM China Release 2.88-CN PROD
202105 | SAM 2.88.5 | 05/20 CHN Time | 05/21 CHN Time | 05/31 CHN Time | CHG0061535- SAM China Month-End Release 2.88.5-UAT
CHG0061536- SAM China Month-End Release 2.88.5-PROD
202105 | FO Local Release 2.88 | 05/06 CHN Time | 05/12 CHN Time | 05/19 CHN Time | CHG0061533-FO China Local Release 2.88-UAT
CHG0061534- FO China Local Release 2.88-PROD
202105 | FO Local Release 2.88.5 | 05/20 CHN Time | 05/21 CHN Time | 05/31 CHN Time | CHG0061531-FO China Local Release 2.88.5-UAT
CHG0061532-FO China Local Release 2.88.5-PROD
202106 | SAM 2.89 | 06/04 CHN Time | 06/10 CHN Time | 06/20 CHN Time | CHG0061609 - SAM China Release 2.89-UAT
CHG0061610 - SAM China Release 2.89-CN PROD
202106 | SAM 2.89.5 | 06/21 CHN Time | 06/22 CHN Time | 06/30 CHN Time | CHG0061611 - SAM China Month-End Release 2.89.5-UAT
CHG0061612 - SAM China Month-End Release 2.89.5-PROD
202106 | FO Local Release 2.89 | 06/04 CHN Time | 06/10 CHN Time | 06/20 CHN Time | CHG0061613 - FO China Local Release 2.89-UAT
CHG0061614 - FO China Local Release 2.89-PROD
202106 | FO Local Release 2.89.5 | 06/21 CHN Time | 06/22 CHN Time | 06/30 CHN Time | CHG0061615 - FO China Local Release 2.89.5-UAT
CHG0061616 - FO China Local Release 2.89.5-PROD

## BCA
ContactID | DirectSellerID | (No column name)
20003387213 | 110000093663 | 赵春雁
20003413337 | 110000096355 | 宋丽娟
20003668134 | 110000114061 | 皮颖辉
20003737035 | 130000025271 | 吴玉洁
20003737061 | 130000025275 | 李书平
20003771105 | 130000026529 | 张春彦
20003895995 | 140000007150 | 郝俊玉
20003483708 | 210000019093 | 孙春燕
20003967779 | 210000030491 | 王锦
20003758113 | 220000015622 | 鞠连霜
20003831059 | 220000017100 | 贾评
20003818584 | 230000014731 | 田辉
20003829815 | 230000015282 | 杨爱华
20003854925 | 230000016138 | 曹春波
20003910677 | 230000017983 | 高速鹰
20003951758 | 310000075406 | 张红
20003957185 | 310000075710 | 王邦英
20003957848 | 310000075771 | 童俊平
20003966653 | 310000075961 | 吴育
20003480788 | 320000050671 | 谢淳而
20003565289 | 320000056865 | 秦捷
20003948685 | 320000093183 | 彭波
20003952255 | 320000093317 | 蒋春院
20003953817 | 320000093656 | 昝海燕
20003960652 | 320000094182 | 郑秀敏
20003962568 | 320000094299 | 马长红
20003967171 | 320000094413 | 张春
20003930590 | 330000097231 | 周红
20003827070 | 340000010816 | 刘素华
20003827613 | 340000010896 | 金燕
20003895629 | 340000013909 | 刘景艳
20003895743 | 340000013929 | 王敏
20003929253 | 340000014113 | 鲍佳清
20003933161 | 340000014157 | 赵银平
20003955276 | 340000014292 | 潘尔红
20003819871 | 370000060457 | 杨琳琳
20003885464 | 410000019832 | 潘洁
20003961221 | 410000021412 | 单慧颖
20003510108 | 420000026414 | 刘群
20003704071 | 420000034607 | 朱芳
20003959063 | 430000039098 | 肖群
20003834689 | 440000143600 | 赵小平
20003818577 | 500000021078 | 桂文惠
20003840231 | 500000021693 | 孙志琼
20003844743 | 500000021748 | 白义纯
20003476785 | 510000015770 | 张学术
20003633026 | 510000021453 | 况英姿
20003850674 | 510000030955 | 王晓妮
20003742139 | 530000019170 | 刘爱华
20003768350 | 530000019518 | 莫妮娜
20003685969 | 650000015766 | 沙莉鹃

## links
发布相关
Octopus | https://deploy/app#/Spaces-1/
Jenkins | http://10.216.212.98/job/FO/job/SAM/job/release/
Service Now | https://marykay.service-now.com/nav_to.do
Create Branch | http://ads.mkcorp.com/DefaultCollection/FrontOffice/_versionControl?path=%24%2FFrontOffice%2FRELEASE
Create Package | http://ads.mkcorp.com/DefaultCollection/FrontOffice/_build
中国日历 | https://mkcorp.sharepoint.com/sites/mkc_IT/sam/frontoffice/default.aspx
美国日历 | https://mkcorp.sharepoint.com/sites/co-usa-ist-dbssamfo/Lists/Calendar/Release.aspx
测试Links
玫琳凯之窗-PROD | https://www.marykayintouch.com.cn/login/login.aspx
玫琳凯之窗-QA | https://qa-site.marykayintouch.com.cn/login/login
玫琳凯之窗-UAT | https://uat-site.marykayintouch.com.cn/login/login
国家企业信用信息公示系统 | http://www.gsxt.gov.cn/index.html
Citrix网页版 | https://citrix.mkcorp.com.cn/vpn/index.html
Splunk系统 | http://mksplunk.chn.mkcorp.com/zh-CN/account/login
工作Link
MK工时系统 | https://marykay.tenrox.net/TEnterprise/index.asp
博彦工时系统 | https://e-cology.beyondsoft.com/login/Login.jsp
新MK文件系统 | https://wiki.chn.mkcorp.com/pages/viewpage.action?pageId=61579549
旧MK文件系统 | https://marykay.atlassian.net/wiki/spaces/FCQKB/overview
MQ_DEV | http://fo-rmq.ebz-chn-dev.mkaws.com:15672
MQ_QA | http://fo-rmq.ebz-chn-qa.mkaws.com:15672
MQ_UAT | http://fo-rmq.ebz-chn-uat.mkaws.com:15672

## Level_Info
BK_CareerLevelID | CareerLevelGroupName | ChinaCareerLevel | CareerLevelDescription
110 | VIP Group | 1 | VIP
110 | VIP Group | 1 | VIP贵宾
120 | VIP Group | 5 | VIP Consultant
120 | VIP Group | 5 | VIP贵宾
130 | VIP Group | 8 | VIP Consultant
130 | VIP Group | 8 | VIP贵宾
220 | Consultant Group | 10 | Beauty Consultant
220 | Consultant Group | 10 | 美容顾问
230 | Consultant Group | 20 | Senior Consultant
230 | Consultant Group | 20 | 资深美容顾问
240 | Consultant Group | 30 | Star Recruiter
240 | Consultant Group | 30 | 明星美容顾问
250 | Consultant Group | 35 | Team Leader
250 | Consultant Group | 35 | 红外套美容顾问
260 | Consultant Group | 40 | Future Director
260 | Consultant Group | 40 | 未来经销商
300 | DIQ Group | 50 | Director in Qualification
300 | DIQ Group | 50 | 准经销商
420 | Director Group | 60 | Sales Director
420 | Director Group | 60 | 经销商
430 | Director Group | 70 | Senior Sales Director
430 | Director Group | 70 | 资深经销商
440 | Director Group | 75 | Future Executive Senior Sales Director
440 | Director Group | 75 | 明星经销商
450 | Director Group | 80 | Executive Senior Sales Director
450 | Director Group | 80 | 执行经销商
460 | Director Group | 85 | Elite Executive Senior Sales Director
460 | Director Group | 85 | 精英执行经销商
500 | NIQ Group |  | National in Qualification
500 | NIQ Group |  | 准首席经销商
620 | NSD Group |  | National Sales Director
620 | NSD Group |  | 首席经销商
630 | NSD Group |  | Senior National Sales Director
630 | NSD Group |  | 资深首席经销商
640 | NSD Group |  | Executive National Sales Director
640 | NSD Group |  | 执行首席经销商
720 | NSD US Group |  | National Sales Director (US Qual)
720 | NSD US Group |  | National Sales Director (US Qual)
730 | NSD US Group |  | Senior National Sales Director (US)
730 | NSD US Group |  | Senior National Sales Director (US)
740 | NSD US Group |  | Executive National Sales Director (US)
740 | NSD US Group |  | Executive National Sales Director (US)
130 | VIP Group |  | VIP Consumer
130 | VIP Group |  | VIP顾客
820 | NSD Retired Group |  | National Sales Director Emeritus
820 | NSD Retired Group |  | 荣誉首席经销商
840 | NSD Retired Group |  | Executive National Sales Director Emeritus
840 | NSD Retired Group |  | 荣誉执行首席经销商
650 | NULL |  | NULL
830 | NSD Retired Group |  | Senior National Sales Director Emeritus
800 | NULL |  | NULL
830 | NSD Retired Group |  | 荣誉资深首席经销商
850 | NSD Retired Group |  | Elite Executive National Sales Director Emeritus
850 | NSD Retired Group |  | 荣誉精英执行首席经销商

## 发布相关人员
Month | Release | Release Coordinator(QA ) | Release Coordinator(UAT ) | FO CRC Support(QA+UAT) | FO CRM Support(QA) | BI Support(QA+UAT) | 常驻人员： | Web Master（Wu yuehao）， DBA（cao rod，zha Leo(需要确认当天谁当班) ）
201801 | SAM 2.48 | Lisa Lei | Lily Cao | Yingyu Chen | Lawrence Wang | Jieyan Qi
201802 | SAM 2.49 | Lisa Lei | Anna Qin | Boole Ma | Jacky Zhang | Jieyan Qi
201803 | SAM 2.50 | Lisa Lei | Lily Cao | Yingyu Chen | Lawrence Wang | Zedle Zhang+Jieyan Qi
201804 | SAM 2.51 | Lily Cao | Anna Qin | Boole Ma | Jacky Zhang | Zedle Zhang+Jieyan Qi
201805 | SAM 2.52 | Lisa Lei | Lily Cao | Yingyu Chen | Lawrence Wang | Zedle Zhang+Jieyan Qi
201806 | SAM 2.53 | Lisa Lei | Lisa Lei | Boole Ma | Jacky Zhang | Zedle Zhang+Jieyan Qi
201807 | SAM 2.54 | Lisa Lei | Lily Cao | Yingyu Chen | Lawrence Wang | Zedle Zhang+Jieyan Qi
201808 | SAM 2.55 | Lily Cao | Xiaoqiang Guo | Boole Ma | Jacky Zhang | Jieyan Qi
201809 | SAM 2.56 | Qiuming Gong | Leila Wei | Yingyu Chen | Lawrence Wang | Zedle Zhang+Jieyan Qi
201810 | SAM 2.57 | Lily Cao | Lily Cao | Boole Ma | Jacky Zhang | Zedle Zhang+Jieyan Qi
201811 | SAM 2.58 | Xiaoqiang Guo | Xiaoqiang Guo | Yingyu Chen | Lawrence Wang | Zedle Zhang+Jieyan Qi
201812 | SAM 2.59 | Qiuming Gong | Qiuming Gong | Boole Ma | Jacky Zhang | Zedle Zhang+Jieyan Qi
201901 | SAM 2.60 | Leila Wei | Leila Wei | Yingyu Chen | Jacky Zhang | Zedle Zhang+Jieyan Qi
201902 | SAM 2.61 | Huiguang Zhu | Huiguang Zhu | Boole Ma | Jacky Zhang | Zedle Zhang+Jieyan Qi
201903 | SAM 2.62 | Xiaoqiang Guo | Xiaoqiang Guo | Yingyu Chen | Jacky Zhang | Zedle Zhang+Jieyan Qi
201904 | SAM 2.63 | Qiuming Gong | Qiuming Gong | Boole Ma | Jacky Zhang | Zedle Zhang+Jieyan Qi
201905 | SAM 2.64 | Leila Wei | Leila Wei | Yingyu Chen | Jacky Zhang | Zedle Zhang+Jieyan Qi
201906 | SAM 2.65 | Huiguang Zhu | Huiguang Zhu | Boole Ma | Jacky Zhang | Zedle Zhang+Jieyan Qi
201907 | SAM 2.66 | Xiaoqiang Guo | Xiaoqiang Guo | Yingyu Chen | Jacky Zhang | Zedle Zhang+Jieyan Qi
201908 | SAM 2.67 | Qiuming Gong | Qiuming Gong | Boole Ma | Jacky Zhang | Zedle Zhang+Jieyan Qi
201909 | SAM 2.68 | Xiaoqiang Guo | Xiaoqiang Guo | Yingyu Chen | Jacky Zhang | Zedle Zhang+Jieyan Qi
201910 | SAM 2.69 | Leila Wei | Leila Wei | Yingyu Chen | Jacky Zhang | Zedle Zhang+Jieyan Qi
201911 | SAM 2.70 | Xiaoqiang Guo | Xiaoqiang Guo | Yingyu Chen | Jacky Zhang | Zedle Zhang+Jieyan Qi
201912 | SAM 2.71 | Leila Wei | Leila Wei | Yingyu Chen | Jacky Zhang | Zedle Zhang+Jieyan Qi

## New Branch
| release | CHN | CHN_PROD | PROD后 | release | CHN | CHN_PROD | PROD后
| 2.75 | 7.61 | 7.6
|  | 2.75CHN | 2.75CHN_PROD
| 2.76 | 7.63 | 7.62 | 7.63
|  | 2.76CHN | 2.76CHN_PROD | 2.76CHN
| 2.77 | 7.65 | 7.64 | 7.65
|  | 2.77CHN | 2.77CHN_PROD | 2.77CHN
| 2.78 | 7.67 | 7.66 | 7.67
|  | 2.78CHN | 2.78CHN_PROD | 2.78CHN
| 2.79 | 7.69 | 7.68 | 7.69
|  | 2.79CHN | 2.79CHN_PROD | 2.79CHN
| 2.80 | 7.71 | 7.70 | 7.71
|  | 2.80CHN | 2.80CHN_PROD | 2.80CHN
10月 | 2.81 | 7.73 | 7.72 | 7.73 | 2.91 | 7.93 | 7.92 | 7.93
|  | 2.81CHN | 2.81CHN_PROD | 2.81CHN |  | 2.91CHN | 2.92CHN_PROD | 2.91CHN
11月 | 2.82 | 7.75 | 7.74 | 7.75 | 2.92 | 7.95 | 7.94 | 7.95
|  | 2.82CHN | 2.82CHN_PROD | 2.82CHN |  | 2.92CHN | 2.94CHN_PROD | 2.92CHN
12月 | 2.83 | 7.77 | 7.76 | 7.77 | 2.93 | 7.97 | 7.96 | 7.97
|  | 2.83CHN | 2.83CHN_PROD | 2.83CHN |  | 2.93CHN | 2.96CHN_PROD | 2.93CHN
| 2.84 | 7.79 | 7.78 | 7.79 | 2.94 | 7.99 | 7.98 | 7.99
|  | 2.84CHN | 2.84CHN_PROD | 2.84CHN |  | 2.94CHN | 2.98CHN_PROD | 2.94CHN
| 2.85 | 7.81 | 7.80 | 7.81 | 2.95
|  | 2.85CHN | 2.85CHN_PROD | 2.85CHN
| 2.86 | 7.83 | 7.82 | 7.83 | 2.96
|  | 2.86CHN | 2.86CHN_PROD | 2.86CHN
| 2.87 | 7.85 | 7.84 | 7.85 | 2.97
|  | 2.87CHN | 2.87CHN_PROD | 2.87CHN
| 2.88 | 7.87 | 7.86 | 7.87 | 2.98
|  | 2.88CHN | 2.88CHN_PROD | 2.88CHN
| 2.89 | 7.89 | 7.88 | 7.89 | 2.99
|  | 2.89CHN | 2.89CHN_PROD | 2.89CHN
| 2.90 | 7.91 | 7.90 | 7.91
|  | 2.90CHN | 2.90CHN_PROD | 2.90CHN

## Sheet1
CHG0057268-SAM China Release 2.81-UAT
CHG0057269-SAM China Release 2.81-CN PROD
CHG0057296-FO China Local Release 2.81-UAT
CHG0057298-FO China Local Release 2.81-PROD
CHG0057299-SAM China Month-End Release 2.81.5-UAT
CHG0057300-SAM China Month-End Release 2.81.5-PROD
CHG0057301-FO China Local Release 2.81.5-UAT
CHG0057302-FO China Local Release 2.81.5-PROD

## 草稿区域
测试接口 | 调用接口完整URL |  | comments |  |  | release | CHN | CHN_PROD
TeamDimContestSummaryInfoGet | AWS | https://folocal-ws.ebz-chn-uat.mkaws.com/fods/CAPInquiry/TeamDimContestSummaryInfo/20017387258?ContactID=20017387258 | AWS接口： |  |  | 2.75 | 2.75CHN | 2.75CHN_PROD
|  |  | 1.原始返回contactID：20017393891人员名称为“全桂交” |  |  |  | 7.61 | 7.6
|  |  | 2.修改AWS数据库，将“全桂交”改为“全桂交_AWS”,后返回内容作出对应变化 |  |  | 2.76 | 2.76CHN | 2.76CHN_PROD
| JDC | http://webservices.chnuat.mktest.com/fods/CAPInquiry/TeamDimContestSummaryInfo/20017387258?ContactID=20017387258 | JDC接口： |  |  |  | 7.63 | 7.62
|  |  | 使用相同参数调用： |  |  | 2.77 | 2.77CHN | 2.77CHN_PROD
|  |  | contactID：20017393891人员名称依旧为为“全桂交” |  |  |  | 7.65 | 7.64
ContestLevelResultGet | AWS | https://folocal-ws.ebz-chn-uat.mkaws.com/fods/Contest/ContestLevelResults/20017405768/1453?contactid=20017405768 | AWS接口： |  |  | 2.78 | 2.78CHN | 2.78CHN_PROD
|  |  | 将ID1453的竞赛的Comment字段修改为“AWS”，调用接口，Comment字段返回为“AWS” |  |  |  | 7.67 | 7.66
| JDC | http://webservices.chnuat.mktest.com/fods/Contest/ContestLevelResults/20017405768/1453?contactid=20017405768 | JDC接口: |  |  | 2.79 | 2.79CHN | 2.79CHN_PROD
|  |  | 相同参数调用，返回数据中，Comment字段为空 |  |  |  | 7.69 | 7.68
ContestLevelResultAndEligibleStatusGet | AWS | https://folocal-ws.ebz-chn-uat.mkaws.com/fods/Contest/ContestLevelResultAndEligibleStatus/20008577223/1/?contactid=20008577223 | AWS接口： |  |  | 2.8 | 2.80CHN | 2.80CHN_PROD
|  |  | 1.将contactid为20008577223的人员名称改为“陈彩霞AWS” |  |  |  | 7.71 | 7.7
| JDC | http://webservices.chnuat.mktest.com/fods/Contest/ContestLevelResultAndEligibleStatus/20008577223/1/?contactid=20008577223 | JDC接口:
相同参数调用，返回数据中，ConsultantName字段依旧为“陈彩霞”
DIQResultGet | AWS | https://folocal-ws.ebz-chn-uat.mkaws.com/fods/Contest/DIQResultInfo/20003263443/201811?contactID=20003263443 | AWS接口：
1.将contactid为20003263443的人员名称改为“张璇_AWS”
| JDC | http://webservices.chnuat.mktest.com/fods/Contest/DIQResultInfo/20003263443/201811?contactID=20003263443 | JDC接口:
相同参数调用，返回数据中，ConsultantName字段依旧为“张璇”
FDIRContestGet | AWS | https://folocal-ws.ebz-chn-uat.mkaws.com/fods/Contest/FDIRContestInfo/20002864231/201811?contactid=20002864231 | AWS接口：
1.原始返回：ResultDictionary下Year=2018，Month=11，YearOfEndDate=2018，MonthOfEndDate=11
且Recruit=2
2. 修改AWS库中数据，再次调用接口，返回值中Recruit值变为3
（将 ConsultantActivityStatus表中ContactID = 20013065239 and BatchID = 544201对应数据的ActivityStatusID改为200
具体语句：update ConsultantActivityStatus set ActivityStatusID =200 where ContactID = 20013065239 and BatchID = 544201）
| JDC | http://webservices.chnuat.mktest.com/fods/Contest/FDIRContestInfo/20002864231/201811?contactid=20002864231 | JDC接口:
相同参数调用，返回内容与AWS完全不一致。
ResultDictionar下Year=2019,Month=1，YearOfEndDate=2019,MonthOfEndDate=1 …
Month | Release | QA | UAT | PROD | Change ID
202007 | SAM 2.78 | 07/03 CHN Time | 07/10 CHN Time | 07/16 DAL Time | CHG0055412 - SAM China Release 2.78-UAT
CHG0055413 - SAM China Release 2.78-CN PROD

## Sheet2
Month | Release | QA | UAT | PROD | Change ID
201807 | SAM 2.54 | 7/5 CHN Time | 7/12 CHN Time | 7/18 DAL Time | CHG0041677-SAM China Release 2.54-UAT
CHG0041678-SAM China Release 2.54 - CN PROD
201807 | SAM 2.54.5 | 7/19 CHN Time | 7/20 CHN Time | 7/31 CHN Time | CHG0041737-SAM China Month-End Release 2.54.5-UAT
CHG0041738-SAM China Month-End Release 2.54.5-PROD
201807 | FO Local Release 2.54 | 7/5 CHN Time | 7/12 CHN Time | 7/18 CHN Time | CHG0041746-FO China Local Release 2.54-UAT
CHG0041747-FO China Local Release 2.54-PROD
201807 | FO Local Release 2.54.5 | 7/19 CHN Time | 7/23 CHN Time | 7/31 CHN Time | CHG0041748-FO China Local Release 2.54.5-UAT
CHG0041749-FO China Local Release 2.54.5-PROD
201808 | SAM 2.55 | 8/6 CHN Time | 8/13 CHN Time | 8/20 DAL Time | CHG0042262-SAM China Release 2.55-UAT
CHG0042351-SAM China Release 2.55-CN PROD
201808 | SAM 2.55.5 | 8/17 CHN Time | 8/21 CHN Time | 8/31 CHN Time | CHG0042360-SAM China Month-End Release 2.55.5-UAT
CHG0042362-SAM China Month-End Release 2.55.5-PROD
201808 | FO Local Release 2.55 | 8/6 CHN Time | 8/13 CHN Time | 8/20 CHN Time | CHG0042385-FO China Local Release 2.55-UAT
CHG0042386 -FO China Local Release 2.55-PROD
201808 | FO Local Release 2.55.5 | 8/17 CHN Time | 8/21 CHN Time | 8/31 CHN Time | CHG0042392-FO China Local Release 2.55.5-UAT
CHG0042397-FO China Local Release 2.55.5-PROD
201809 | SAM 2.56 | 9/7 CHN Time | 9/13 CHN Time | 9/19 DAL Time | CHG0043052-SAM China Release 2.56-UAT
CHG0043054-SAM China Release 2.56-CN PROD
201809 | SAM 2.56.5 | 9/20 CHN Time | 9/21 CHN Time | 9/30 CHN Time | CHG0043057-SAM China Month-End Release 2.56.5-UAT
CHG0043059-SAM China Month-End Release 2.56.5-PROD
201809 | FO Local Release 2.56 | 9/7 CHN Time | 9/13 CHN Time | 9/19 CHN Time | CHG0043064-FO China Local Release 2.56-UAT
CHG0043066-FO China Local Release 2.56-PROD
201809 | FO Local Release 2.56.5 | 9/19 CHN Time | 9/21 CHN Time | 9/30 CHN Time | CHG0043055 - FO China Local Release 2.56.5-UAT
CHG0043058 - FO China Local Release 2.56.5-PROD
201810 | SAM 2.57 | 10/4 CHN Time | 10/10 CHN Time | 10/16 DAL Time | CHG0043738 - SAM China Release 2.57-UAT
CHG0043816 - SAM China Release 2.57-CN PROD
201810 | SAM 2.57.5 | 10/17 CHN Time | 10/18 CHN Time | 10/31 CHN Time | CHG0043777 - SAM China Month-End Release 2.57.5-UAT
CHG0043778 - SAM China Month-End Release 2.57.5-PROD
201810 | FO Local Release 2.57 | 10/4 CHN Time | 10/11 CHN Time | 10/22 CHN Time | CHG0043733 - FO China Local Release 2.57-UAT
CHG0043736 - FO China Local Release 2.57-PROD
201810 | FO Local Release 2.57.5 | 10/23 CHN Time | 10/24 CHN Time | 10/31 CHN Time | CHG0043737 - FO China Local Release 2.57.5-UAT
CHG0043739 - FO China Local Release 2.57.5-PROD
201811 | SAM 2.58 | 11/9 CHN Time | 11/14 CHN Time | 11/16 DAL Time | CHG0044699 - SAM China Release 2.58-UAT
CHG0044700 - SAM China Release 2.58-CN PROD
201811 | SAM 2.58.5 | 11/20 CHN Time | 11/22 CHN Time | 11/30 CHN Time | CHG0044701 - SAM China Month-End Release 2.58.5-UAT
CHG0044702 - SAM China Month-End Release 2.58.5-PROD
201811 | FO Local Release 2.58 | 11/7 CHN Time | 11/14 CHN Time | 11/19 CHN Time | CHG0044692 - FO China Local Release 2.58-UAT
CHG0044693- FO China Local Release 2.58-PROD
201811 | FO Local Release 2.58.5 | 11/20 CHN Time | 11/22 CHN Time | 11/30 CHN Time | CHG0044695 - FO China Local Release 2.58.5-UAT
CHG0044696- FO China Local Release 2.58.5-PROD
201812 | SAM 2.59 | 12/5 CHN Time | 12/12 CHN Time | 12/18 DAL Time | CHG0045289 - SAM China Release 2.59-UAT
CHG0045290 - SAM China Release 2.59-CN PROD
201812 | SAM 2.59.5 | 12/19 CHN Time | 12/24 CHN Time | 12/31 CHN Time | CHG0045292 - SAM China Month-End Release 2.59.5-UAT
CHG0045294 - SAM China Month-End Release 2.59.5-PROD
201812 | FO Local Release 2.59 | 12/5 CHN Time | 12/12 CHN Time | 12/19 CHN Time | CHG0045291 - FO China Local Release 2.59-UAT
CHG0045295- FO China Local Release 2.59-PROD
201812 | FO Local Release 2.59.5 | 12/19 CHN Time | 12/24 CHN Time | 12/31 CHN Time | CHG0045296 - FO China Local Release 2.59.5-UAT
CHG0045297- FO China Local Release 2.59.5-PROD
201901 | SAM 2.60 | 1/4/2019 CHN Time | 1/11 CHN Time | 1/17 DAL Time | CHG0045463 - SAM China Release 2.60-UAT
CHG0045464 - SAM China Release 2.60-CN PROD
201901 | SAM 2.60.5 | 1/18 CHN Time | 1/22 CHN Time | 11/31 CHN Time | CHG0045466 - SAM China Month-End Release 2.60.5-UAT
CHG0045467 - SAM China Month-End Release 2.60.5-PROD
201901 | FO Local Release 2.60 | 1/4/2019 CHN Time | 1/11 CHN Time | 1/17 CHN Time | CHG0045518 - FO China Local Release 2.60-UAT
CHG0045519 - FO China Local Release 2.60-PROD
201901 | FO Local Release 2.60.5 | 1/18 CHN Time | 1/22 CHN Time | 11/31 CHN Time | CHG0045520 - FO China Local Release 2.60.5-UAT
CHG0045521 - FO China Local Release 2.60.5-PROD
201902 | SAM 2.61 | 2/11/2019 CHN Time | 2/15 CHN Time | 2/21 DAL Time | CHG0046106 - SAM China Release 2.61-UAT
CHG0046107 - SAM China Release 2.61-CN PROD
201902 | SAM 2.61.5 | 2/22 CHN Time | 2/25 CHN Time | 2/28 CHN Time | CHG0046109 - SAM China Month-End Release 2.61.5-UAT
CHG0046110 - SAM China Month-End Release 2.61.5-PROD
201902 | FO Local Release 2.61 | 2/11/2019 CHN Time | 2/15 CHN Time | 2/21 CHN Time | CHG0046105 - FO China Local Release 2.61-UAT
CHG0046111 - FO China Local Release 2.61-PROD
201902 | FO Local Release 2.61.5 | 2/22 CHN Time | 2/25 CHN Time | 2/28 CHN Time | CHG0046112 - FO China Local Release 2.61.5-UAT
CHG0046113 - FO China Local Release 2.61.5-PROD
201903 | SAM 2.62 | 3/5 CHN Time | 3/12 CHN Time | 3/19 DAL Time | CHG0046881 - SAM China Release 2.62-UAT
CHG0046882 - SAM China Release 2.62-CN PROD
201903 | SAM 2.62.5 | 3/20 CHN Time | 3/25 CHN TIME | 3/31 CHN TIME | CHG0046883 - SAM China Month-End Release 2.62.5-UAT
CHG0046884 - SAM China Month-End Release 2.62.5-PROD
201903 | FO Local Release 2.62 | 3/5 CHN Time | 3/12 CHN Time | 3/19 CHN Time | CHG0046885 - FO China Local Release 2.62-UAT
CHG0046886 - FO China Local Release 2.62-PROD
201903 | FO Local Release 2.62.5 | 3/20 CHN Time | 3/25 CHN TIME | 3/31 CHN TIME | CHG0046887 - FO China Local Release 2.62.5-UAT
CHG0046888 - FO China Local Release 2.62.5-PROD
201904 | SAM 2.63 | 4/3 CHN Time | 4/11 CHN Time | 4/16 DAL Time | CHG0047225 - SAM China Release 2.63-UAT
CHG0047226 - SAM China Release 2.63-CN PROD
201904 | SAM 2.63.5 | 4/17 CHN Time | 4/22 CHN Time | 4/30 CHN Time | CHG0047227 - SAM China Month-End Release 2.63.5-UAT
CHG0047228 - SAM China Month-End Release 2.63.5-PROD
201904 | FO Local Release 2.63 | 4/3 CHN Time | 4/11 CHN Time | 4/16 CHN Time | CHG0047220 - FO China Local Release 2.63-UAT
CHG0047221 - FO China Local Release 2.63-PROD
201904 | FO Local Release 2.63.5 | 4/17 CHN Time | 4/22 CHN Time | 4/30 CHN Time | CHG0047222 - FO China Local Release 2.63.5-UAT
CHG0047223 - FO China Local Release 2.63.5-PROD
201905 | SAM 2.64 | 5/6 CHN Time | 5/13 CHN Time | 5/21 DAL Time | CHG0047765-SAM China Release 2.64-UAT
CHG0047766-SAM China Release 2.64-CN PROD
201905 | SAM 2.64.5 | 5/22 CHN Time | 5/27 CHN Time | 5/31 CHN Time | CHG0047767-SAM China Month-End Release 2.64.5-UAT
CHG0047768-SAM China Month-End Release 2.64.5-PROD
201905 | FO Local Release 2.64 | 5/6 CHN Time | 5/13 CHN Time | 5/21 CHN Time | CHG0047761 - FO China Local Release 2.64-UAT
CHG0047762 - FO China Local Release 2.64-PROD
201905 | FO Local Release 2.64.5 | 5/22 CHN Time | 5/27 CHN Time | 5/31 CHN Time | CHG0047763 - FO China Local Release 2.64.5-UAT
CHG0047764 - FO China Local Release 2.64.5-PROD
201906 | SAM 2.65 | 06/05 CHN Time | 06/11 CHN Time | 06/18 DAL Time | CHG0048655 - SAM China Release 2.65-UAT
CHG0048656 - SAM China Release 2.65-CN PROD
201906 | SAM 2.65.5 | 06/19 CHN Time | 06/24 CHN Time | 06/30 CHN Time | CHG0048658 - SAM China Month-End Release 2.65.5-UAT
CHG0048659 - SAM China Month-End Release 2.65.5-PROD
201906 | FO Local Release 2.65 | 06/04 CHN Time | 06/11 CHN Time | 06/18 CHN Time | CHG0048651 - FO China Local Release 2.65-UAT
CHG0048652 - FO China Local Release 2.65-PROD
201906 | FO Local Release 2.65.5 | 06/19 CHN Time | 06/24 CHN Time | 06/30 CHN Time | CHG0048653 - FO China Local Release 2.65.5-UAT
CHG0048654 - FO China Local Release 2.65.5-PROD
201907 | SAM 2.66 | 07/03 CHN Time | 07/10 CHN Time | 07/17 DAL Time | CHG0049008 - SAM China Release 2.66-UAT
CHG0049009 - SAM China Release 2.66-CN PROD
201907 | SAM 2.66.5 | 07/18 CHN Time | 07/23 CHN Time | 07/31 CHN Time | CHG0049011 - SAM China Month-End Release 2.66.5-UAT
CHG0049013 - SAM China Month-End Release 2.66.5-PROD
201907 | FO Local Release 2.66 | 07/03 CHN Time | 07/10 CHN Time | 07/17 CHN Time | CHG0049004 - FO China Local Release 2.66-UAT
CHG0049005 - FO China Local Release 2.66-PROD
201907 | FO Local Release 2.66.5 | 07/18 CHN Time | 07/23 CHN Time | 07/31 CHN Time | CHG0049006 - FO China Local Release 2.66.5-UAT
CHG0049007 - FO China Local Release 2.66.5-PROD
201908 | SAM 2.67 | 08/06 CHN Time | 08/13 CHN Time | 08/20 DAL Time | CHG0049766 - SAM China Release 2.67-UAT
CHG0049767 - SAM China Release 2.67-CN PROD
201908 | SAM 2.67.5 | 08/21 CHN Time | 08/26 CHN Time | 08/31 CHN Time | CHG0049768 - SAM China Month-End Release 2.67.5-UAT
CHG0049769 - SAM China Month-End Release 2.67.5-PROD
201908 | FO Local Release 2.67 | 08/06 CHN Time | 08/13 CHN Time | 08/20 CHN Time | CHG0049760 - FO China Local Release 2.67-UAT
CHG0049761 - FO China Local Release 2.67-PROD
201908 | FO Local Release 2.67.5 | 08/21 CHN Time | 08/26 CHN Time | 08/31 CHN Time | CHG0049763 - FO China Local Release 2.67.5-UAT
CHG0049764 - FO China Local Release 2.67.5-PROD
201909 | SAM 2.68 | 09/05 CHN Time | 09/12 CHN Time | 09/19 DAL Time | CHG0050045 - SAM China Release 2.68-UAT
CHG0050046 - SAM China Release 2.68-CN PROD
201909 | SAM 2.68.5 | 09/20 CHN Time | 09/24 CHN Time | 09/30 CHN Time | CHG0050047 - SAM China Month-End Release 2.68.5-UAT
CHG0050049 - SAM China Month-End Release 2.68.5-PROD
201909 | FO Local Release 2.68 | 09/05 CHN Time | 09/12 CHN Time | 09/19 CHN Time | CHG0050057 - FO China Local Release 2.68-UAT
CHG0050058 - FO China Local Release 2.68-PROD
201909 | FO Local Release 2.68.5 | 09/20 CHN Time | 09/24 CHN Time | 09/30 CHN Time | CHG0050059 - FO China Local Release 2.68.5-UAT
CHG0050060 - FO China Local Release 2.68.5-PROD
201910 | SAM 2.69 | 10/04 CHN Time | 10/10 CHN Time | 10/17 DAL Time | CHG0050879 - SAM China Release 2.69-UAT
CHG0050880 - SAM China Release 2.69-CN PROD
201910 | SAM 2.69.5 | 10/18 CHN Time | 10/23 CHN Time | 10/31 CHN Time | CHG0050881 - SAM China Month-End Release 2.69.5-UAT
CHG0050882 - SAM China Month-End Release 2.69.5-PROD
201910 | FO Local Release 2.69 | 10/04 CHN Time | 10/10 CHN Time | 10/17 CHN Time | CHG0050874 - FO China Local Release 2.69-UAT
CHG0050875 - FO China Local Release 2.69-PROD
201910 | FO Local Release 2.69.5 | 10/18 CHN Time | 10/23 CHN Time | 10/31 CHN Time | CHG0050876 - FO China Local Release 2.69.5-UAT
CHG0050877 - FO China Local Release 2.69.5-PROD
201911 | SAM 2.70 | 11/05 CHN Time | 11/12 CHN Time | 11/19 DAL Time | CHG0051307 - SAM China Release 2.70-UAT
CHG0051308 - SAM China Release 2.70-CN PROD
201911 | SAM 2.70.5 | 11/20 CHN Time | 11/25 CHN Time | 11/30 CHN Time | CHG0051309 - SAM China Month-End Release 2.70.5-UAT
CHG0051310 - SAM China Month-End Release 2.70.5-PROD
201911 | FO Local Release 2.70 | 11/05 CHN Time | 11/12 CHN Time | 11/19 CHN Time | CHG0051311 - FO China Local Release 2.70-UAT
CHG0051312 - FO China Local Release 2.70-PROD
201911 | FO Local Release 2.70.5 | 11/20 CHN Time | 11/25 CHN Time | 11/30 CHN Time | CHG0051313 - FO China Local Release 2.70.5-UAT
CHG0051314 - FO China Local Release 2.70.5-PROD
201912 | SAM 2.71 | 12/05 CHN Time | 12/12 CHN Time | 12/18 DAL Time | CHG0051770 - SAM China Release 2.71-UAT
CHG0051771 - SAM China Release 2.71-CN PROD
201912 | SAM 2.71.5 | 12/19 CHN Time | 12/24 CHN Time | 12/31 CHN Time | CHG0051772 - SAM China Month-End Release 2.71.5-UAT
CHG0051773 - SAM China Month-End Release 2.71.5-PROD
201912 | FO Local Release 2.71 | 12/05 CHN Time | 12/12 CHN Time | 12/18 CHN Time | CHG0051774 - FO China Local Release 2.71-UAT
CHG0051775 - FO China Local Release 2.71-PROD
201912 | FO Local Release 2.71.5 | 12/19 CHN Time | 12/24 CHN Time | 12/31 CHN Time | CHG0051777 - FO China Local Release 2.71.5-UAT
202001 | SAM 2.72 | 01/07 CHN Time | N/A | N/A | N/A
202001 | SAM 2.72.5 | 01/20 CHN Time | 01/22 CHN Time | 01/31 CHN Time | CHG0052405 - SAM China Month-End Release 2.72.5-UAT
CHG0052406 - SAM China Month-End Release 2.72.5-PROD
202001 | FO Local Release 2.72 | 01/07 CHN Time | 01/14 CHN Time | 01/20 CHN Time | CHG0052401 - FO China Local Release 2.72-UAT
CHG0052402 - FO China Local Release 2.72-PROD
202001 | FO Local Release 2.72.5 | 01/20 CHN Time | 01/22 CHN Time | 01/31 CHN Time | CHG0052403 - FO China Local Release 2.72.5-UAT
CHG0052404 - FO China Local Release 2.72.5-PROD
202002 | SAM 2.73 | 02/05 CHN Time | 02/12 CHN Time | 02/19 DAL Time | CHG0053017 - SAM China Release 2.73-UAT
CHG0053018 - SAM China Release 2.73-CN PROD
202002 | SAM 2.73.5 | 02/20 CHN Time | 02/25 CHN Time | 02/29 CHN Time | CHG0053019 - SAM China Month-End Release 2.73.5-UAT
CHG0053020 - SAM China Month-End Release 2.73.5-PROD
202002 | FO Local Release 2.73 | 02/05 CHN Time | 02/12 CHN Time | 02/19 CHN Time | CHG0053022 - FO China Local Release 2.73-UAT
CHG0053023 - FO China Local Release 2.73-PROD
202002 | FO Local Release 2.73.5 | 02/20 CHN Time | 02/25 CHN Time | 02/29 CHN Time | CHG0053024 - FO China Local Release 2.73.5-UAT
CHG0053025 - FO China Local Release 2.73.5-PROD
202003 | SAM 2.74 | 03/05 CHN Time | 03/12 CHN Time | 03/18 DAL Time | CHG0053361 - SAM China Release 2.74-UAT
CHG0053362 - SAM China Release 2.74-CN PROD
202003 | SAM 2.74.5 | 03/19 CHN Time | 03/24 CHN Time | 03/31 CHN Time | CHG0053365 - FO China Local Release 2.74-UAT
CHG0053366 - FO China Local Release 2.74-PROD
202003 | FO Local Release 2.74 | 03/05 CHN Time | 03/12 CHN Time | 03/18 CHN Time | CHG0053363 - SAM China Month-End Release 2.74.5-UAT
CHG0053364 - SAM China Month-End Release 2.74.5-PROD
202003 | FO Local Release 2.74.5 | 03/19 CHN Time | 03/24 CHN Time | 03/31 CHN Time | CHG0053367 - FO China Local Release 2.74.5-UAT
CHG0053368 - FO China Local Release 2.74.5-PROD
202004 | SAM 2.75 | 04/03 CHN Time | 04/10 CHN Time | 04/20 DAL Time | CHG0053732 - SAM China Release 2.75-UAT
CHG0053734 - SAM China Release 2.75-CN PROD
202004 | SAM 2.75.5 | 04/21 CHN Time | 04/24 CHN Time | 04/30 CHN Time | CHG0053736 - SAM China Month-End Release 2.75.5-UAT
CHG0053737 - SAM China Month-End Release 2.75.5-PROD
202004 | FO Local Release 2.75 | 04/03 CHN Time | 04/10 CHN Time | 04/20 CHN Time | CHG0053738 - FO China Local Release 2.75-UAT
CHG0053739 - FO China Local Release 2.75-PROD
202004 | FO Local Release 2.75.5 | 04/21 CHN Time | 04/24 CHN Time | 04/30 CHN Time | CHG0053740 - FO China Local Release 2.75.5-UAT
CHG0053741 - FO China Local Release 2.75.5-PROD
202005 | SAM 2.76 | 05/05 CHN Time | 05/12 CHN Time | 05/20 DAL Time | CHG0054252 - SAM China Release 2.76-UAT
CHG0054253 - SAM China Release 2.76-CN PROD
202005 | SAM 2.76.5 | 05/21 CHN Time | 05/25 CHN Time | 05/31 CHN Time | CHG0054254 - SAM China Month-End Release 2.76.5-UAT
CHG0054231 - SAM China Month-End Release 2.76.5-PROD
202005 | FO Local Release 2.76 | 05/05 CHN Time | 05/12 CHN Time | 05/20 CHN Time | CHG0054255 - FO China Local Release 2.76-UAT
CHG0054256 - FO China Local Release 2.76-PROD
202005 | FO Local Release 2.76.5 | 05/21 CHN Time | 05/25 CHN Time | 05/31 CHN Time | CHG0054257 - FO China Local Release 2.76.5-UAT
CHG0054258 - FO China Local Release 2.76.5-PROD
202006 | SAM 2.77 | 06/03 CHN Time | 06/10 CHN Time | 06/18 DAL Time | CHG0054969 - SAM China Release 2.77-UAT
CHG0054970 - SAM China Release 2.77-CN PROD
202006 | SAM 2.77.5 | 06/19 CHN Time | 06/23 CHN Time | 06/30 CHN Time | CHG0054971 - SAM China Month-End Release 2.77.5-UAT
CHG0054972 - SAM China Month-End Release 2.77.5-PROD
202006 | FO Local Release 2.77 | 06/03 CHN Time | 06/10 CHN Time | 06/18 CHN Time | CHG0054973 - FO China Local Release 2.77-UAT
CHG0054974 - FO China Local Release 2.77-PROD
202006 | FO Local Release 2.77.5 | 06/19 CHN Time | 06/23 CHN Time | 06/30 CHN Time | CHG0054976 - FO China Local Release 2.77.5-UAT
CHG0054977 - FO China Local Release 2.77.5-PROD
202007 | SAM 2.78 | 07/03 CHN Time | 07/10 CHN Time | 07/16 DAL Time | CHG0055412 - SAM China Release 2.78-UAT
CHG0055413 - SAM China Release 2.78-CN PROD
202007 | SAM 2.78.5 | 07/17 CHN Time | 07/21 CHN Time | 07/31 CHN Time | CHG0055414 - SAM China Month-End Release 2.78.5-UAT
CHG0055415 - SAM China Month-End Release 2.78.5-PROD
202007 | FO Local Release 2.78 | 07/03 CHN Time | 07/10 CHN Time | 07/16 CHN Time | CHG0055416 - FO China Local Release 2.78-UAT
CHG0055417 - FO China Local Release 2.78-PROD
20200 | FO Local Release 2.78.5 | 07/17 CHN Time | 07/21 CHN Time | 07/31 CHN Time | CHG0055418 - FO China Local Release 2.78.5-UAT
CHG0055419 - FO China Local Release 2.78.5-PROD
202008 | SAM 2.79 | 08/05 CHN Time | 08/12 CHN Time | 08/19 DAL Time | CHG0056020 - SAM China Release 2.79-UAT
CHG0056022 - SAM China Release 2.79-CN PROD
202008 | SAM 2.79.5 | 08/20 CHN Time | 08/26 CHN Time | 08/31 CHN Time | CHG0056023 - SAM China Month-End Release 2.79.5-UAT
CHG0056024 - SAM China Month-End Release 2.79.5-PROD
202008 | FO Local Release 2.79 | 08/05 CHN Time | 08/12 CHN Time | 08/19 DAL Time | CHG0056025 - FO China Local Release 2.79-UAT
CHG0056026 - FO China Local Release 2.79-PROD
202008 | FO Local Release 2.79.5 | 08/20 CHN Time | 08/26 CHN Time | 08/31 CHN Time | CHG0056028 - FO China Local Release 2.79.5-UAT
CHG0056029 - FO China Local Release 2.79.5-PROD
202009 | SAM 2.80 | 09/03 CHN Time | 09/10 CHN Time | 09/17 DAL Time | CHG0056646 - SAM China Release 2.80-UAT
CHG0056578 - SAM China Release 2.80-CN PROD
202009 | SAM 2.80.5 | 09/18 CHN Time | 09/24 CHN Time | 09/30 CHN Time | CHG0056595- SAM China Month-End Release 2.80.5-UAT
CHG0056600 - SAM China Month-End Release 2.80.5-PROD
202009 | FO Local Release 2.80 | 09/03 CHN Time | 09/10 CHN Time | 09/17 DAL Time | CHG0056579- FO China Local Release 2.80-UAT
CHG0056593- FO China Local Release 2.80-PROD
202009 | FO Local Release 2.80.5 | 09/18 CHN Time | 09/24 CHN Time | 09/30 CHN Time | CHG0056598- FO China Local Release 2.80.5-UAT
CHG0056599 - FO China Local Release 2.80.5-PROD
202010 | SAM 2.81 | 10/09 CHN Time | 10/14 CHN time | 10/20 DAL Time | CHG0057268-SAM China Release 2.81-UAT
CHG0057269-SAM China Release 2.81-CN PROD
202010 | SAM 2.81.5 | 10/21 CHN Time | 10/26 CHN Time | 10/31 CHN Time | CHG0057299-SAM China Month-End Release 2.81.5-UAT
CHG0057300-SAM China Month-End Release 2.81.5-PROD
202010 | FO Local Release 2.81 | 10/09 CHN Time | 10/14 CHN time | 10/20 DAL Time | CHG0057296-FO China Local Release 2.81-UAT
CHG0057298-FO China Local Release 2.81-PROD
202010 | FO Local Release 2.81.5 | 10/21 CHN Time | 10/26 CHN Time | 10/31 CHN Time | CHG0057301-FO China Local Release 2.81.5-UAT
CHG0057302-FO China Local Release 2.81.5-PROD
202011 | SAM 2.82 | 11/04 CHN Time | 11/11 CHN Time | 11/19 DAL Time | CHG0057800-SAM China Release 2.82-UAT
CHG0057801-SAM China Release 2.82-CN PROD
202011 | SAM 2.82.5 |  |  |  | CHG0057802-SAM China Month-End Release 2.82.5-UAT
CHG0057803-SAM China Month-End Release 2.82.5-PROD
202011 | FO Local Release 2.82 | 11/04 CHN Time | 11/11 CHN Time | 11/19 CHN Time | CHG0057805-FO China Local Release 2.82-UAT
CHG0057809- FO China Local Release 2.82-PROD
202011 | FO Local Release 2.82.5 |  |  |  | CHG0057808-FO China Local Release 2.82.5-UAT
CHG0057810- FO China Local Release 2.82.5-PROD
202012 | SAM 2.83 | 12/03 CHN Time | 12/10 CHN Time | 12/17 DAL Time | CHG0058444 - SAM China Release 2.83-UAT
CHG0058445 - SAM China Release 2.83-CN PROD
202012 | SAM 2.83.5 | 12/18 CHN Time | 12/24 CHN Time | 12/31 CHN Time | CHG0058446 - SAM China Month-End Release 2.83.5-UAT
CHG0058447 - SAM China Month-End Release 2.83.5-PROD
202012 | FO Local Release 2.83 | 12/03 CHN Time | 12/10 CHN Time | 12/17 CHN Time | CHG0058448 - FO China Local Release 2.83-UAT
CHG0058449 - FO China Local Release 2.83-PROD
202012 | FO Local Release 2.83.5 | 12/18 CHN Time | 12/24 CHN Time | 12/31 CHN Time | CHG0058450 - FO China Local Release 2.83.5-UAT
202101 | SAM 2.84 | 01/06 CHN Time | 01/13 CHN Time | 01/20 CHN Time | CHG0059099 - SAM China Release 2.84-UAT
CHG0059100 - SAM China Release 2.84-CN PROD
202101 | SAM 2.84.5 | 01/21 CHN Time | 01/26 CHN Time | 01/31 CHN Time | CHG0059101 - SAM China Month-End Release 2.84.5-UAT
CHG0059102 - SAM China Month-End Release 2.84.5-PROD
202101 | FO Local Release 2.84 | 01/06 CHN Time | 01/13 CHN Time | 01/20 CHN Time | CHG0059103 - FO China Local Release 2.84-UAT
CHG0059104 - FO China Local Release 2.84-PROD
202101 | FO Local Release 2.84.5 | 01/21 CHN Time | 01/26 CHN Time | 01/31 CHN Time | CHG0059105 - FO China Local Release 2.84.5-UAT
CHG0059106 - FO China Local Release 2.84.5-PROD
202102 | SAM 2.85 | 02/03 CHN Time | 02/08 CHN Time | 02/18 CHN Time | CHG0059508 - SAM China Release 2.85-UAT
CHG0059509 - SAM China Release 2.85-CN PROD
202102 | SAM 2.85.5 | 02/19 CHN Time | 02/24 CHN Time | 02/28 CHN Time | CHG0059510 - SAM China Month-End Release 2.85.5-UAT
CHG0059511 - SAM China Month-End Release 2.85.5-PROD
202102 | FO Local Release 2.85 | 02/03 CHN Time | 02/08 CHN Time | 02/18 CHN Time | CHG0059512 - FO China Local Release 2.85-UAT
CHG0059513 - FO China Local Release 2.85-PROD
202102 | FO Local Release 2.85.5 | 02/19 CHN Time | 02/24 CHN Time | 02/28 CHN Time | CHG0059514 - FO China Local Release 2.85.5-UAT
CHG0059515 - FO China Local Release 2.85.5-PROD
202103 | SAM 2.86 | 03/03 CHN Time | 03/10 CHN Time | 03/17 CHN Time | CHG0060045 - SAM China Release 2.86-UAT
CHG0060046 - SAM China Release 2.86-CN PROD
202103 | SAM 2.86.5 | 03/18 CHN Time | 03/19 CHN Time | 03/31 CHN Time | CHG0060047 - SAM China Month-End Release 2.86.5-UAT
CHG0060048 - SAM China Month-End Release 2.86.5-PROD
202103 | FO Local Release 2.86 | 03/03 CHN Time | 03/10 CHN Time | 03/17 CHN Time | CHG0060049 - FO China Local Release 2.86-UAT
CHG0060050 - FO China Local Release 2.86-PROD
202103 | FO Local Release 2.86.5 | 03/18 CHN Time | 03/19 CHN Time | 03/31 CHN Time | CHG0060051 - FO China Local Release 2.86.5-UAT
CHG0060052 - FO China Local Release 2.86.5-PROD
202104 | SAM 2.87 | 04/06 CHN Time | 04/13CHN Time | 04/20 DAL Time | CHG0060573-SAM China Release 2.87-UAT
CHG0060572-SAM China Release 2.87-CN PROD
202104 | SAM 2.87.5 | 04/21 CHN Time | 04/22 CHN Time | 04/30 DAL Time | CHG0060575-SAM China Month-End Release 2.87.5-UAT
CHG0060576-SAM China Month-End Release 2.87.5-PROD
202104 | FO Local Release 2.87 | 04/06 CHN Time | 04/13CHN Time | 04/20 DAL Time | CHG0060577-FO China Local Release 2.87-UAT
CHG0060579-FO China Local Release 2.87-PROD
202104 | FO Local Release 2.87.5 | 04/21 CHN Time | 04/22 CHN Time | 04/30 DAL Time | CHG0060581-FO China Local Release 2.87.5-UAT
CHG0060582-FO China Local Release 2.87.5-PROD
202105 | SAM 2.88 | 05/06 CHN Time | 05/12 CHN Time | 05/19 CHN Time | CHG0060813 - SAM China Release 2.88-UAT
CHG0060814 - SAM China Release 2.88-CN PROD
202105 | SAM 2.88.5 | 05/20 CHN Time | 05/21 CHN Time | 05/31 CHN Time | CHG0061535- SAM China Month-End Release 2.88.5-UAT
CHG0061536- SAM China Month-End Release 2.88.5-PROD
202105 | FO Local Release 2.88 | 05/06 CHN Time | 05/12 CHN Time | 05/19 CHN Time | CHG0061533-FO China Local Release 2.88-UAT
CHG0061534- FO China Local Release 2.88-PROD
202105 | FO Local Release 2.88.5 | 05/20 CHN Time | 05/21 CHN Time | 05/31 CHN Time | CHG0061531-FO China Local Release 2.88.5-UAT
CHG0061532-FO China Local Release 2.88.5-PROD
202106 | SAM 2.89 | 06/04 CHN Time | 06/10 CHN Time | 06/17 DAL Time | CHG0061609 - SAM China Release 2.89-UAT
CHG0061610 - SAM China Release 2.89-CN PROD
202106 | SAM 2.89.5 | 06/18 CHN Time | 06/21 CHN Time | 06/30 DAL Time | CHG0061611 - SAM China Month-End Release 2.89.5-UAT
CHG0061612 - SAM China Month-End Release 2.89.5-PROD
202106 | FO Local Release 2.89 | 06/04 CHN Time | 06/10 CHN Time | 06/17 DAL Time | CHG0061613 - FO China Local Release 2.89-UAT
CHG0061614 - FO China Local Release 2.89-PROD
202106 | FO Local Release 2.89.5 | 06/18 CHN Time | 06/21 CHN Time | 06/30 DAL Time | CHG0061615 - FO China Local Release 2.89.5-UAT
CHG0061616 - FO China Local Release 2.89.5-PROD

## BCA-issue
郝俊玉 | 140000007150
郝俊玉 | 140000007150