## links
发布相关
Octopus | https://deploy/app#/Spaces-1/
Jenkins | http://10.216.212.98/job/FO/job/SAM/job/release/
Service Now | https://marykay.service-now.com/nav_to.do
Create Branch | http://ads.mkcorp.com/DefaultCollection/FrontOffice/_versionControl?path=%24%2FFrontOffice%2FRELEASE
Create Package | http://ads.mkcorp.com/DefaultCollection/FrontOffice/_build
中国日历 | https://mkcorp.sharepoint.com/sites/mkc_IT/sam/frontoffice/default.aspx
美国日历 | https://mkcorp.sharepoint.com/sites/co-usa-ist-dbssamfo/Lists/Calendar/Release.aspx
测试Links
玫琳凯之窗-PROD | https://www.marykayintouch.com.cn/login/login.aspx
玫琳凯之窗-QA | https://qa-site.marykayintouch.com.cn/login/login
玫琳凯之窗-UAT | https://uat-site.marykayintouch.com.cn/login/login
国家企业信用信息公示系统 | http://www.gsxt.gov.cn/index.html
Citrix网页版 | https://citrix.mkcorp.com.cn/vpn/index.html
Splunk系统 | http://mksplunk.chn.mkcorp.com/zh-CN/account/login
工作Link
MK工时系统 | https://marykay.tenrox.net/TEnterprise/index.asp
博彦工时系统 | https://e-cology.beyondsoft.com/login/Login.jsp
新MK文件系统 | https://wiki.chn.mkcorp.com/pages/viewpage.action?pageId=61579549
旧MK文件系统 | https://marykay.atlassian.net/wiki/spaces/FCQKB/overview
MQ_DEV | http://fo-rmq.ebz-chn-dev.mkaws.com:15672
MQ_QA | http://fo-rmq.ebz-chn-qa.mkaws.com:15672
MQ_UAT | http://fo-rmq.ebz-chn-uat.mkaws.com:15672

## deploy_plan
Month | Release | QA | UAT | PROD | Change ID
202103 | SAM 2.86 | 03/03 CHN Time | 03/10 CHN Time | 03/17 CHN Time | CHG0060045 - SAM China Release 2.86-UAT
CHG0060046 - SAM China Release 2.86-CN PROD
202103 | SAM 2.86.5 | 03/18 CHN Time | 03/19 CHN Time | 03/31 CHN Time | CHG0060047 - SAM China Month-End Release 2.86.5-UAT
CHG0060048 - SAM China Month-End Release 2.86.5-PROD
202103 | FO Local Release 2.86 | 03/03 CHN Time | 03/10 CHN Time | 03/17 CHN Time | CHG0060049 - FO China Local Release 2.86-UAT
CHG0060050 - FO China Local Release 2.86-PROD
202103 | FO Local Release 2.86.5 | 03/18 CHN Time | 03/19 CHN Time | 03/31 CHN Time | CHG0060051 - FO China Local Release 2.86.5-UAT
CHG0060052 - FO China Local Release 2.86.5-PROD
202104 | SAM 2.87 | 04/06 CHN Time | 04/13CHN Time | 04/20 DAL Time | CHG0060573-SAM China Release 2.87-UAT
CHG0060572-SAM China Release 2.87-CN PROD
202104 | SAM 2.87.5 | 04/21 CHN Time | 04/22 CHN Time | 04/30 DAL Time | CHG0060575-SAM China Month-End Release 2.87.5-UAT
CHG0060576-SAM China Month-End Release 2.87.5-PROD
202104 | FO Local Release 2.87 | 04/06 CHN Time | 04/13CHN Time | 04/20 DAL Time | CHG0060577-FO China Local Release 2.87-UAT
CHG0060579-FO China Local Release 2.87-PROD
202104 | FO Local Release 2.87.5 | 04/21 CHN Time | 04/22 CHN Time | 04/30 DAL Time | CHG0060581-FO China Local Release 2.87.5-UAT
CHG0060582-FO China Local Release 2.87.5-PROD
202105 | SAM 2.88 | 05/06 CHN Time | 05/12 CHN Time | 05/19 CHN Time | CHG0060813 - SAM China Release 2.88-UAT
CHG0060814 - SAM China Release 2.88-CN PROD
202105 | SAM 2.88.5 | 05/20 CHN Time | 05/21 CHN Time | 05/31 CHN Time | CHG0061535- SAM China Month-End Release 2.88.5-UAT
CHG0061536- SAM China Month-End Release 2.88.5-PROD
202105 | FO Local Release 2.88 | 05/06 CHN Time | 05/12 CHN Time | 05/19 CHN Time | CHG0061533-FO China Local Release 2.88-UAT
CHG0061534- FO China Local Release 2.88-PROD
202105 | FO Local Release 2.88.5 | 05/20 CHN Time | 05/21 CHN Time | 05/31 CHN Time | CHG0061531-FO China Local Release 2.88.5-UAT
CHG0061532-FO China Local Release 2.88.5-PROD
202106 | SAM 2.89 | 06/04 CHN Time | 06/10 CHN Time | 06/20 DAL Time | CHG0061609 - SAM China Release 2.89-UAT
CHG0061610 - SAM China Release 2.89-CN PROD
202106 | SAM 2.89.5 | 06/21 CHN Time | 06/22 CHN Time | 06/30 DAL Time | CHG0061611 - SAM China Month-End Release 2.89.5-UAT
CHG0061612 - SAM China Month-End Release 2.89.5-PROD
202106 | FO Local Release 2.89 | 06/04 CHN Time | 06/10 CHN Time | 06/20 DAL Time | CHG0061613 - FO China Local Release 2.89-UAT
CHG0061614 - FO China Local Release 2.89-PROD
202106 | FO Local Release 2.89.5 | 06/21 CHN Time | 06/22 CHN Time | 06/30 DAL Time | CHG0061615 - FO China Local Release 2.89.5-UAT
CHG0061616 - FO China Local Release 2.89.5-PROD
202107 | SAM 2.90 | 07/05 CHN Time | 07/12 CHN Time | 07/19 CHN Time | CHG0062609- SAM China Release 2.90-UAT
CHG0062611- SAM China Release 2.90-CN PROD
202107 | SAM 2.90.5 | 07/20 CHN Time | 07/21 CHN Time | 07/31 CHN Time | CHG0062612 - SAM China Month-End Release 2.90.5-UAT
CHG0062613- SAM China Month-End Release 2.90.5-PROD
202107 | FO Local Release 2.90 | 07/05 CHN Time | 07/12 CHN Time | 07/19 CHN Time | CHG0062614- FO China Local Release 2.90-UAT
CHG0062615 - FO China Local Release 2.90-PROD
202107 | FO Local Release 2.90.5 | 07/20 CHN Time | 07/21 CHN Time | 07/31 CHN Time | CHG0062616 - FO China Local Release 2.90.5-UAT
CHG0062617- FO China Local Release 2.90.5-PROD

## level_info
BK_CareerLevelID | CareerLevelGroupName | ChinaCareerLevel | CareerLevelDescription
110 | VIP Group | 1 | VIP贵宾
120 | VIP Group | 5 | VIP Consultant/VIP贵宾
130 | VIP Group | 8 | VIP Consultant/VIP贵宾
220 | Consultant Group | 10 | Beauty Consultant/美容顾问
230 | Consultant Group | 20 | Senior Consultant/资深美容顾问
240 | Consultant Group | 30 | Star Recruiter/明星美容顾问
250 | Consultant Group | 35 | Team Leader/红外套美容顾问
260 | Consultant Group | 40 | Future Director/未来经销商
300 | DIQ Group | 50 | Director in Qualification/准经销商
420 | Director Group | 60 | Sales Director/经销商
430 | Director Group | 70 | Senior Sales Director/资深经销商
440 | Director Group | 75 | Future Executive Senior Sales Director/明星经销商
450 | Director Group | 80 | Executive Senior Sales Director/执行经销商
460 | Director Group | 85 | Elite Executive Senior Sales Director/精英执行经销商
500 | NIQ Group | 87 | National in Qualification/准首席经销商
620 | NSD Group | 90 | National Sales Director/首席经销商
630 | NSD Group | 92 | Senior National Sales Director/资深首席经销商
640 | NSD Group | 95 | Executive National Sales Director/执行首席经销商
720 | NSD US Group |  | National Sales Director (US Qual)
730 | NSD US Group |  | Senior National Sales Director (US)
740 | NSD US Group |  | Executive National Sales Director (US)
820 | NSD Retired Group | 99 | National Sales Director Emeritus/荣誉首席经销商
830 | NSD Retired Group | 99 | Senior National Sales Director Emeritus/荣誉资深首席经销商
840 | NSD Retired Group | 99 | Executive National Sales Director Emeritus/荣誉执行首席经销商
850 | NSD Retired Group | 99 | Elite Executive National Sales Director Emeritus/荣誉精英执行首席经销商

## others
00030$00030bB
7426983826Tao!
BC: 000000000063 (ywms_2019/职级90)
foapp Dlguc65o
foapp Blguw62o
foapp Twf45w62o
oaWQ6uNaAlegV6M2siw7Ja56wGJ0
UAT:CHG0045109
PROD:CHG0045111
splnuk:eventtype="pcf_app" "MKOS.EmpApp.qa" "access_token"